“Sustainable Financing and Management of Eastern Caribbean Marine Ecosystems” Project

Full Size Project (FSP)

Terms of Reference for a Monitoring & Evaluation Specialist

1.  Introduction

This consultancy focuses on the third component of the “Sustainable Financing and Management of Eastern Caribbean Marine Ecosystems Project,” the aim of which is to establish a robust, transparent, user friendly, and cost-effective monitoring and evaluation plan to determine the status of and trends in the protected area systems of participating OECS member states which can serve as a decision support tool for natural resource managers and policymakers.  The plan will integrate management effectiveness as well as biophysical and socio-economic information from the entire protected area network for the Eastern Caribbean and its various management institutions into one regional information system. (Please refer to the Project Appraisal Document in Annex A for a more detailed treatment of the Component and the project generally).

In designing an information system to house and analyze the data necessary for the effective management of MPAs, the type of data collected needs to be determined foremost. A preliminary report by Mr. John Waugh entitled “Report on Monitoring and Evaluation Options for the Sustainable Financing and Management of Eastern Caribbean Marine Ecosystems for the OECS Project” prepared during the project’s preparation phase assesses conservation evaluation and management effectiveness approaches, identifies which are in use in the Eastern Caribbean, identifies gaps in data collection, and recommends a realistic core set of data and indicators to assess the effectiveness of site-based conservation interventions.  Mr. Waugh’s report is attached hereto as Annex B.  Mr. Waugh’s report lays out a set of recommendations for designing and implementing an effective M&E system which includes  (i) using a core set of management indicators from OPAAL (Annex C); (ii) using an expanded set of indicators which take into account drivers of change, species representation and distribution, ecological vulnerability and the social context. These include coral reef and coastal zone management indicators (Annex 3 of the report); and (iii) options for an updatable, interactive information management system to house all this data.

2. Consultancy Objectives

The objectives of this consultancy are:

Objective 1: Develop and reach a consensus on a set of biophysical and socio-economic indicators that will be used to monitor the status of and trends in the marine protected area systems in the region.

Objective 2: Draft TOR to TNC and World Bank and selected PA managers for how plan can be demonstrated in one location.

Objective 3: Prepare a written “Eco-Regional Monitoring M&E Plan” which documents Object 1 and provides critical feasibility lessons from outcomes of Objective 2.  Further details are described in “Scope of Work” below.

3. Scope of Work – Activities

To accomplish the above-referenced objectives, the consultant will work in coordination with TNC, the World Bank, and stakeholders in each of the five participating countries to complete the following tasks:

Task 1 - Work plan

- Develop a work plan to be reviewed and approved by TNC on how the objectives of the consultancy will be accomplished.

Task 2: Background Research

- Quickly, but thoroughly review and assess existing measures of indicators that have been collected or monitoring plans that exist and have existed which could compliment this project.

  - Review and consider a set of background documents to the project, including the project’s document (PAD) and Mr. Waugh’s report.

  - investigate recent changes in the state of monitoring and evaluation to include, for example, a review of other monitoring projects and protocols being implemented or utilized in the region, an assessment of their respective pros and cons and opportunities for collaboration, a recommendation or ranking of the best protocol(s) or partnership opportunities, and any other relevant suggestions as appropriate.  E.g, as mentioned above, CERMES at UWI has employed Socioeconomic Monitoring techniques modified for the Caribbean that follow the SocMon Framework.

  - Determine if sources of secondary data have the scope and frequency of collection to be adequate for the purposes of this project.  This includes whether past SocMon efforts can be built upon or if other socioeconomic monitoring is occurring and what biophysical data is being monitored.

  - Identify any gaps in data that should be filled by primary data collection and if so, how this gap can be filled simply and at minimal cost, particularly Marine Protected Area (MPA) data.

Task 3

- Conduct in-country consultations with experts/data collection communities in each participating country to assess your findings and vet your preliminary recommendations.

Task 4

Develop a draft M&E Plan for the Project which is a comprehensive assessment of what indicators are to be used, why, and how this data is to be obtained, converted and displayed for decision support.  The Plan should:

  - Focus on the choices for key indicators and why. The assessment should include discussions related to availability and completeness of data, relevancy of data, compatibility of data with the monitoring system, level of effort, etc

  - Include a comparative analysis of the estimated costs of data collection of biophysical and socio-economic monitoring under various monitoring protocols, as well as the costs associated with the expected set of indicators to be adopted by the Project, giving due regard to the availability of equipment and expertise.  Besides biophysical and socio-economic data, other dimensions such as governance and cultural aspects should be included, as these may influence the ecological and social outcomes.

  - Assess the sustainability of the Plan.  Discuss how the data would be maintained and updated, the roles and responsibilities for collection and other tasks associated with maintaining the plan (institutions, university, individuals, government, etc) and how often.

  - Assess the level of effort (labor, cost, time) required to obtain the databases, update them, and convert them into a format to go into the monitoring system. Where data has to be collected, assess the level of effort needed to do so.

  - Include a list of key persons/government staff in participating countries with responsibility for MPA monitoring and data management (who could be invited to participate in workshops).

  - Contain a well-researched list of possible partner agencies, research institutions, and/or donors working regionally to monitor protected area and ensure sustainability of monitoring efforts over the long term. (e.g. the Caribbean Sea Commission, Caribbean Large Marine Ecosystem Project, Organization of Eastern Caribbean States, Global Parks, Future of Reefs in a Changing Environment (FORCE), the University of the West Indies, the International Union for the Conservation of Nature (specifically the Biodiversity and Protected Area Management (BioPAMA) project), CaribSave, the World Bank (specifically its GeoNode Project), The Nature Conservancy, and the National Oceanic and Atmospheric Administration)

  - Contains a draft budget under the Plan in light of constraints.

  - Contains an assessment of a possible pilot country to demonstrate how the M&E Plan and data collection system could be implemented, as well as draft Terms of Reference for a consultancy to conduct demonstration activities.

  - Contains an assessment of capacity to maintain and manage the database as well as the cost of training in relationship to database input, management, etc if required

  - Collaborate with the “platform” consultant to ensure an understanding of how indicator data is to be collected, inputted and displayed by the system.

Task 5

- Conduct a small in-country working session to give feedback on the approach and build consensus.

Participants will discuss options and approaches, and receive stakeholder feedback and input on the various approaches, specifically looking at the context for the country and which approaches may or may not work.  Participants would complete a “decision document” – designed by the consultant – identifying the decisions to be taken at the regional workshop with respect to the indicators to be tracked, for example, and who in country would need to authorize decisions, etc.

Task 6:  Attend and lead the discussions on an eco-regional workshop

Eco-Regional Workshop Activities

The aim of the workshop is to reach a consensus on a set of core indicators which will result in a common dataset useful for eco-regional assessments.  These will ultimately populate the data management framework developed by the project.

- Work with TNC to organize and develop the program/agenda and list of presenters and participants for an Eco-Regional Monitoring workshop.

- Play a lead role, along with The Conservancy, in facilitating an eco-regional monitoring workshop. During the workshop, the consultant will make presentations and hold discussions detailing his or her draft M&E  plan and providing background information on how it fits with work already undertaken and other regional and national MPA monitoring and data management initiatives.  He or she, along with the Conservancy and other partners, will also lead or participate in focused discussions of the suggested set of indicators, their rationales, and how the collection of the indicators can presented and consumed by decision makers, in order to help stakeholders to reach a consensus on a limited set of core indicators which will result in a common dataset useful for eco-regional assessments.

- Prepare a brief workshop report summarizing outcomes of discussions.

Task 7: Post-Workshop Activities

- Integrate feedback from workshop into M&E plan, as needed.

- Finalize estimate of costs of data collection for of biophysical and socio-economic monitoring in consideration of final core set of indicators, the availability of equipment and expertise, and compatibility with existing monitoring systems.

- Within 30 days, submit a final version of the M&E plan, which includes but is not limited to the best way to monitor trends in biophysical and socio-economic conditions in MPAs using the chosen indicators, and an indicative budget for the actions identified.

- Conduct final in-country consultations to explain to in-country partners the outcomes of the eco-regional monitoring workshop and to identify the next steps for in-country implementation.

4.  Reports and Deliverables

The contractor is expected to make periodic reports to TNC. Reports should be concise and limited to significant issues related to the scope of work.  Deliverables expected from the consultant include:

|  | Deliverables | Due Date on or before |
| --- | --- | --- |
| 1 | A detailed work plan for contract activities and deliverables, containing a concise annotated outline, description of approach (methodology), timeline, and budget for materials. | Month 1 |
| 2 | Decisions Document (for use in National Consultations, described above). | Month 2 |
| 3 | Conduct first series of in-country consultations (one per participating country), payment will issue after the last of the five consultations. | Month 2 |
| 4 | A draft M&E plan (described above) | Month 3 |
| 5 | PowerPoint and printed materials for use at the Eco-regional Monitoring Workshop / presentation at workshop | Month 3 / 4 |
| 6 | Workshop Report | Month 4 |
| 7 | Conduct second series of in-country consultations, payment will issue after last of the five consultations. | Month 5 |
| 8 | A final version of the M&E plan integrating feedback from the workshop | End of Month 6 |

(All the outputs shall be submitted as electronic documents in MS Word and as hard copies to The Nature Conservancy)

5. Qualifications

- An in-depth knowledge of social science and biological research methods including experiment design, biological data collection, data analysis and interpretation, presentation, statistical and research theory and techniques, and population measurement techniques, as acquired through at least five years of post-qualification experience.

- A basic knowledge of data platforms and an in depth knowledge of data input requirements

- A demonstrated ability to work with diverse stakeholders in collaborative data collection.

- A Master’s degree with relevant work experience of 8 or more years or a Ph.D in a relevant area (relevant areas will include social science and/or biological sciences  with in depth experience working in the natural/social science/environment arena).

- An in-depth knowledge of ecosystem management, particularly data acquisition and use of indicators, both biophysical and socioeconomic.

- Ability to develop methods of data collection, interpret data and analyze environmental information to apply solutions, guidelines and policy to field problems.

- An ability to effectively interact and communicate with government officials, regional, intergovernmental organizations, and the multi-lateral donor community in the Eastern Caribbean.

- Excellent organizational, written, and verbal communication skills in English.

- Ability to work independently and be a team player.

- Ability to communicate on a regular basis via email and phone.

- This recruitment is open to regional and international consultants.

6. Length of Contract

The duties of the role will take between six and eight months to complete.

Individuals interested in providing the services described above should send letters of interest and curricula vitae to The Nature Conservancy (rbovino@tnc.org).

Annex A – Project Appraisal Document

Annex B – Report on Monitoring and Evaluation Options

Annex C – MPA Management Effectiveness Monitoring Scorecard

The report interprets “realistic” as taking into account budget constraints and limits in technical capacity common to protected areas and of particular concern in the Eastern Caribbean.